## Sprint Backlog
Priority | Number | PBI | Tasks | Not Started | In Progress | Completed
High (1st) | 2 | As a Product Owner, I want the system to process IRV elections without errors so that the product is available to Election Officials to process election files. Acceptance Criteria: The system processes and displays the correct winner for the IR election file. Ties between candidates are broken with a fair coin toss. Definition of Done: IR information is read in from the file correctly and the winner is displayed correctly. Audit files are generated. Effort: Medium | Fix bug coming from checkWinner2() function | X
|  |  | Invalidated Ballots mechanisms not working correctly | X
|  |  | Write additional IR tests + Complete Testing Logs for IR | X
High (1st) | 3 | As a Product Owner, I want the system to process OPL elections without errors so that the product is available to Election Officials to process election files. Acceptance Criteria: The system processes and displays the correct winner for the OPL election file. Ties between parties are broken with a fair coin toss. Definition of Done: OPL information is read in from the file correctly and the winner is displayed correctly. Audit files are generated. Appropriate testing for all system components is completed along with documentation. Effort: Medium | Add tie breaker case to handle candidates who have same number of votes. This will be done inside both first, second and third round allocations | X
|  |  | Write additional OPL tests where two candidates have the same number of votes, but only 1 seat + Complete Testing Logs for OPL | X
High (2nd) | 4 | As an election official, I want to determine winners from an MPO Election because it is an election type mandated by the Secretary of State. Acceptance Criteria: I know the winner for an MPO election. Can run on CSE Lab Machines Definition of Done: MPO information is read in from the file correctly and the winner is displayed correctly. Should provide fair and unbiased results. Appropriate testing for all system components is completed along with documentation. Effort: Large | Add an MPOElection type class that inherits from Election Type. Add functionality to support MPO voting. | X
|  |  | Add tests for MPO + Testing logs | X
| 5 | As an election official, I want to upload MPO ballots through a .csv file because that is how we receive election files from an election center. Acceptance Criteria: The system can automatically process information for an MPO election through a formatted csv file. Definition of Done: The system can process MPO csv files and populate data structures with the correct information. Source code is updated and appropriate documentation and testing is completed. Effort: Medium | Read in MPO csv file and and initialize MPO election object correctly (NOTE: file format for candidates + their parties is different from IR and OPL's (see write up) | X
|  |  | Add tests for reading MPO file + Testing Logs | X
| 7 | As an election official, I want to be able to view the stats from MPO Election on my screen so that I know who won and who lost and the constituents who voted know how well their candidate did in the election. Acceptance Criteria: I can view the election stats after I input an MPO Election Data file into the system for vote counting. Definition of Done: The percentage of votes each candidate received, are displayed on the user’s screen correctly after the system has processed the election data file and counted the votes. Effort: Medium | Display election type, election date, number of candidates, vote count of each candidate | X
|  |  | Write testing logs for the display (Manual verification) | X
X
X
Medium | 9 | As an election official, I want the system to verify the validity of IRV ballots and then accordingly eliminate and store invalidated ballots so that they match state election official regulations. | Find all invalidated ballots | X
|  |  | Store invalidated ballots | X
|  |  | Add tests for invalidated ballots + associated testing logs | X

## Product Backlog
Number | Item | Acceptance Criteria | Definition of Done | Effort
1 | As an election official, I want the system to be as hands-off as possible so that there is minimal room for human error. | All election details are read in from the file other than the date of the election. | Source code is updated appropriately to read in the election date. Test that election details (type, #of candidates, etc.) are read in from the file and populated into the internal data structures correctly. | Small
2 | As a Product Owner, I want the system to process IRV elections without errors so that the product is available to Election Officials to process election files. | The system processes and displays the correct winner for the IR election file. Ties between candidates are broken with a fair coin toss | IR information is read in from the file correctly and the winner is displayed correctly. Audit files are generated
3 | As a Product Owner, I want the system to process OPL elections without errors so that the product is available to Election Officials to process election files
4 | As an election official, I want to determine winners from an MPO Election because it is an election type mandated by the Secretary of State.